## TILL Core
Task
Requirement & Design
Understanding the Device Interface Specification - Verifone
Understanding the Device Interface Specification - Ingenico
Scope document, Discussions & Signoff
Design - Usecase, Sequence Design
API Specifications
Test Plan
Design Review & Signoff
Development
Core Implementation
Transaction Request
Transaction Response
Configuration
Configuration Base Implementation
Connection Manager Implementation
Base Connection Manager
Serial Connection
Ethernet/Wifi Connection
Bluetooth Connection
Verifone Device Interface
Core Request Encoding Module
Core Response Encoding Module
Status/Error Handling
Transaction Module
Device Check Status
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Sale
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Pre-auth Sale
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Pre-auth completion
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Pre-auth cancellation
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Refund
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Void
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Offline TIP
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
EMI Sale
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Settlement
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Ingenico Device Interface
Core Request Encoding Module
Core Response Encoding Module
Status/Error Handling
Transaction Module
Device Check Status
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Sale
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Pre-auth Sale
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Pre-auth completion
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Pre-auth cancellation
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Refund
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Void
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Offline TIP
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
EMI Sale
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
Settlement
Request Encoding
Response Handling & Parsing
Transaction Status & Error Handling
JNI Interface
Implementing Core JNI Classes
API for device status check
API for transaction processing
Device Check Status
Sale
Pre-auth Sale
Pre-auth completion
Pre-auth cancellation
Refund
Void
Offline TIP
EMI Sale
Settlement
API for Configuration
Error Handling
.NET Interoperability
Implementing Core Wrapper Classes
Marshalling
Unmarshalling
API for device status check
API for transaction processing
Device Check Status
Sale
Pre-auth Sale
Pre-auth completion
Pre-auth cancellation
Refund
Void
Offline TIP
EMI Sale
Settlement
API for Configuration
Error Handling

## SDK & Sample App
Java & Web Interface | .NET Interface
Design | Design
Web API design document | .NET API design document
Design - Usecase, Sequence design | Design - Usecase, Sequence design
Review & Signoff | Review & Signoff
Development | Development
Core API Service Implementation | Core API Service Implementation
Request Handling | Request Handling
Response Handling | Response Handling
Connection Manager Callback Implementation | Connection Manager Callback Implementation
Serial Interface | Serial Interface
Ethernet/Wifi Interface | Ethernet/Wifi Interface
Bluetooth Interface | Bluetooth Interface
API for transaction processing | API for transaction processing
Device Check Status | Device Check Status
Sale | Sale
Pre-auth Sale | Pre-auth Sale
Pre-auth completion | Pre-auth completion
Pre-auth cancellation | Pre-auth cancellation
Refund | Refund
Void | Void
Offline TIP | Offline TIP
EMI Sale | EMI Sale
Settlement | Settlement
API for Configuration | API for Configuration
Error Handling | Error Handling
Sample Application Development | Sample Application Development
Unit testing | Unit testing
Android | iOS
Design | Design
API design document (Java API will be used) | iOS API design document
Design - Usecase, Sequence design | Design - Usecase, Sequence design
Review & Signoff | Review & Signoff
Development | Development
Core API Service Implementation | Core API Service Implementation
Request Handling | Request Handling
Response Handling | Response Handling
Connection Manager Callback Implementation | Connection Manager Callback Implementation
Serial Interface | Serial Interface
Ethernet/Wifi Interface | Ethernet/Wifi Interface
Bluetooth Interface | Bluetooth Interface
API for transaction processing | API for transaction processing
Device Check Status | Device Check Status
Sale | Sale
Pre-auth Sale | Pre-auth Sale
Pre-auth completion | Pre-auth completion
Pre-auth cancellation | Pre-auth cancellation
Refund | Refund
Void | Void
Offline TIP | Offline TIP
EMI Sale | EMI Sale
Settlement | Settlement
API for Configuration | API for Configuration
Error Handling | Error Handling
Sample Application Development | Sample Application Development
Unit testing | Unit testing

## Assumptions
Assumptions:
TILL library will be designed and implemented from scratch
TILL Library to be supported for Linux, Windows, Android and IOS
Scope is currently considered for Verifone and Ingenico, PAX will considered after the application development.
DCC is out of scope for TILL Integration (DCC Selection on POS & DCC on Euronet pad connected to EDC device will continue to support)
Library is implemented in Java
API structure for Linux, Windows, Android will remain same
Only existing devices deployed in field are considered for first library release
Communication mode to devices is initially considered to be USB/Serial
Dependencies
Ingenico payment application binaries to test the TILL lib.
VeriFone payment application binaries to test the TILL lib.
Interface specification from TILL to EDC (VeriFone, Ingenico)
Host connectivity details